## Course Plan & Schedule
Dates are in PST
Session Time is between 9:00 PM ~ 11:00 PM PST
Sencha Touch 2.0 & RoR Course Plan and Progress Tracker
Sl.No. | Topic | Planned |  | Actual |  | Status | Notes
|  | Date (PST) | Hours | Date | Hours
1 | Development Environment Setup | 2012-08-02 | 2
Sencha Touch SDK
Local website pointing to Sencha Touch SDK Folder
Eclipse Setup
Emulator (Ripple)
Google Code to keep the course material, Source Code & Project Management etc.
Github & Heroku for RoR hosting (Optional, not required immediately)
Cloud registration - Phone Gap build (Optional, not required immediately. This can be done offline)
Introduction to Case Study Application.
Creating Sencha Touch Project for Case Study Application using Sencha SDK (Scaffolding)
Sencha MVC (JavaScript MVC framewok) and how Sencha is superior than JQUERY Mobile
2 | Architecture | 2012-08-05 | 2
Multi Layer Solution Architecture for Mobile Apps Development
User Interface Layer using Sencha Touch
Server Side Code in Ruby On Rails (can be anything i.e. Sinatra in Ruby, Nancy in .NET, Php, JSP etc)
RESTful Services
Mobile Client to RoR Server communication - JSON data
A sample RoR RESTful service demo (exporting RoR controller as RESTapi which is natively supported in RoR)
Case Study Application Building
Application Launch UI
Login UI
Home UI
Integrating Login & Home with Mock JSON DB
3 | Data / Domain Model (JSON) / Entities | 2012-08-07 | 2
User
Table Of Contents
Issues
Festival (Parent, Child hierarchy)
4 | Monthly Issues UI | 2012-08-09 | 2
List View
Filter by Year & Month
TOC UI (LIST)
Link Issues with TOC
5 | Festivals UI | 2012-08-12 | 2
Nested List
Details View
Custom Theme for List View
Custom Theme for Details View
6 | Writing RESTful API in RoR and Deploy in Heroku | 2012-08-14 | 2
Authentication
Issues (Monthly Issues)
TOC
Festivals
7 | Backend Integration With Ruby On Rails REST API | 2012-08-16 | 2
Removing Hardcoded / Mock Data with Ruby
8 | Build & Package | 2012-08-19 | 2
PhoneGap, Sencha & Test Flight
PhoneGap build setup
Android Build (pk file)
PhoneGap (Using PhoneGap cloud build)
Sencha Build (MAC & Windows)
Deploy in Android
9 | Build & Package | 2012-08-21 | 2
IOS Build (ipa file)
Test Flight setup
Deploy in IOS devices (iPhone, Ipod Touch, Ipad)
10 | Advanced Concepts & Miscellaneous | 2012-08-23 | 2
Performance i.e. Offline / Online Mode (Leverage Cache through local storage)
Sync
Auto Login (Through Settings UI)
11 | Puch Notification | 2012-08-26 | 2
Sencha.IO
Pubnub
12 | Custom Theme | 2012-08-28 | 2
SASS & COMPASS framework
13 | Exercise & Review, Sencha API Walk through | 2012-08-30 | 2
14 | Exercise & Review, Sencha API Walk through | 2012-09-02 | 2

## Case Study App - Biz Functions
Whats Going On <Company / City or choice of yours>
Sl.No. | Modules
1 | Application Launch
2 | Login
3 | Home / Dashboard
4 | Settings
5 | Monthly Issues
6 | Table Of Contents
7 | City Map
8 | Festivals
9 | Theater Movies
10 | TV Movies
11 | Performance
12 | Exhibitions
13 | Announcements
14 | Emergency Hospitals
15 | Search

## Technology Coverage Matrix
Sl.No. | Technical Aspects Of Sencha / RoR | Business Function
|  | Application Launch | Login | Home | Settings | Monthly Issues | TOC | City Map | Festivals | Theater Movies | TV Movies | Performance | Exhibitions | Announcements | Emergency Hospitals | Search
Sencha
| Sencha Bootstrapper | 1 |  |  | 1
| Sencha Container Control |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Sencha Panel Control |  | 1
| Sencha Tab Bar / Panel |  |  | 1
| Sencha Icons |  |  | 1
| Launch Icon | 1
| Sencha Tab Panel |  |  | 1
| Sencha List View |  |  |  |  | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1
| Sencha Nested List |  |  |  |  | 1 |  |  | 1
| Sencha Card Layout |  |  | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Sencha Navigation View |  |  |  |  | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Sencha Disclosure/Tap |  |  |  |  | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Sencha Map API | [6 empty] | 1
| Sencha Component |  | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Sencha Template |  |  |  |  | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Sencha Store | 1 |  |  |  | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1
Local Storage
| Ajax |  | 1
| Sencha Views | 1 |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Sencha Models (aka entities) | 1 | 1 |  |  | 1 | 1
| Sencha Validations |  | 1
| Sencha Controllers | 1 |  | 1 |  | 1
| Sencha Event Listerners inside controller |  |  |  |  | 1
Sencha Grouper
Sencha Sorting
Sencha Animation
| Slide L-R |  |  | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Slide T-B & B-T | [14 empty] | 1
| Sencha Message Box (Pop up panel) |  | 1
| Push Notification | [14 empty] | 1
Ruby On Rails
| Ruby Models | 1 |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Ruby Controllers | 1 |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
SQLITE DB Access
| Export Controller as RESTful Services |  | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Phone Gap / Sencha Build
PhoneGap build
| PhoneGap | 1
app.JSON

## HW & SW Req
Mac / Windows Machine
Eclipse with Android & IOS SDK
Jetbrains WebStrom Trial/ VS.NET Web Developer Express (Optional)
Google Chrome with following addons
Ripple Emulator
Firefox with following Addons
Firebug
REST Client
Tortoise SVN Client
Sqlite (Optional if Ruby)
Ruby On Rails gems
NancyFx
SAAS
COMPASS
Sencha SDK
RavenDB (Preferable in cloud)
Cloud Environment
GitHub (optional if ruby)
Heroku Rails Web Server (optional if ruby)
Appharbour (Optional If .Net)
CodePlex (Optional if .Net)
RavenDBHQ (Optional if .Net)
Google Play (For production)
Apple IOS Developer (Dev/Test & Production)
TestFlight (Dev & Test)
Sencha.IO
Device for live testing
Android Smart Phone (Ginger Bird)
IOS (3gs & plus)
Ipod Touch
Iphone
Ipad

## Url References
CSS3 / HTML5
http://channel9.msdn.com/Series/HTML5-CSS3-Fundamentals-Development-for-Absolute-Beginners
Google Code Subversion Repository
https://wgo-in-sencha.googlecode.com/svn/trunk/
Username | vmmobility
Password | Nm7Qm9WQ4yy7
Note:
Vmoksha code will be in the Trunk
Hung code will be in the branch
List Pagenation
http://stackoverflow.com/questions/7131864/sencha-touch-how-to-handle-long-lists-on-ios
http://stackoverflow.com/questions/7321446/sencha-list-paging-plugin
http://stackoverflow.com/questions/7183111/sencha-touch-list-append-new-results-from-store-load

## Wire Frame - Splash
| Size | 320 X 460
in Matsuyama City
http://corp.softcoin.com/
Wgo
Whats Going On
by Vmokshagroup.com

## Wire Frame - Login
Matsuyama City
Wgo

## Wire Frame - Home
in Matsuyama City
Wgo
Settings
Issues
City Map

## Wire Frame - Festival List
Matsuyama City
|  | 1 WED | UKAI (Cormorant Fishing) Jun'21 - Sep'13
Festivals July 2012 |  |  | The tradition of fishing with cormorants goes back
|  | 3 MON | UKAI (Cormorant Fishing) Jun'21 - Sep'13
The tradition of fishing with cormorants goes back
|  | 7 TUE | UKAI (Cormorant Fishing) Jun'21 - Sep'13
The tradition of fishing with cormorants goes back
|  | 23 MON | UKAI (Cormorant Fishing) Jun'21 - Sep'13
The tradition of fishing with cormorants goes back
|  | 29 SUN | UKAI (Cormorant Fishing) Jun'21 - Sep'13
The tradition of fishing with cormorants goes back
|  | 30 MON | UKAI (Cormorant Fishing) Jun'21 - Sep'13
The tradition of fishing with cormorants goes back
Wgo

## Wire Frame - Festival Detail
Matsuyama City
Ukai (Cormorant Fishing) |  | UKAI (Cormorant Fishing) On the Hiji-kawa (river) In Ozu City
|  | Date | June 1-Sept. 20
|  | Time | 18:30-21:00
|  | Telephone | 089-456-9087
The tradition of fishing with cormorants goes back at least a thousand years. In Ozu it started as a tourist attraction in 1957 and it is one of the three most famous ukai spots in Japan. The fishing is done from boats called ubune, which is lit by torches as it sails down the Hiji-kawa, the river that runs through Ozu. Cormorant fishermen called usho, beat the sides of the boats to encourage the trained ormorants to catch fish. They are pulled by long strings attached to rings around the birds' necks which prevent them from swallowing the fish. The torchlight attracts fish. You can watch this from special sightseeing boats called yakatabune. A meal is served while on the yakatabune. The fare is as follows:
Wgo